## Sheet1
Week | Duration | Progress
1 | 13 Feb - 15 Feb | Research about Brushless DC Motor, Driver and Controller
2 | 17 Feb - 22 Feb | Research about Brushless DC Motor, Driver and Controller
3 | 24 Feb - 29 Feb | Simulation of Brushless DC Motor, Driver and Controller in Proteus, MATLAB and PSIM
4 | 2 Mar - 7 Mar | Hardware Implementation of 3 phase Inverter with transformer isolation
5 | 9 Mar - 14 Mar | Hardware Implementation of 3 phase Inverter with transformer isolation
6 | 16 Mar - 21 Mar | Research about 3 phase inverter with optical isolation and Voltage Level Shifter
7 | 23 Mar - 28 Mar | Simulation of 3 phase inverter with optical isolation and Voltage Level Shifter in PSIM
8 | 30 Mar - 4 Apr | Modeling and Simulation of Brushless DC Motor, Driver and Controller Design in MATLAB
9 | 6 Apr - 11 Apr | Detailed Report of Brushless DC Motor Modeling, Inverter and Controller
10 | 13 Apr - 15 Apr | Detailed Report of Brushless DC Motor Modeling, Inverter and Controller